## UX Review
SumGrid — Product UX/UI Review
Based on full source-code audit of all 3 screens, 7 components, theme, and game logic
Area | Finding | Severity | Recommendation
ONBOARDING & FIRST-TIME EXPERIENCE
Onboarding Flow | 3-puzzle mandatory sequence with no skip option. Users who understand the concept are forced through all 3 launches across 3 separate days before reaching the real game. | Critical | Add a 'Skip tutorial' link. Let advanced users jump to Home immediately. Consider completing onboarding in a single session instead of 3 days.
Rule Explanation | No explicit rules screen or tooltip. Title says 'Let's learn SumGrid' but there's no text explaining what row/column sums mean or how to play. | Critical | Add a brief rules overlay or coach marks on the first puzzle explaining: fill cells so each row and column hits its target sum.
Onboarding Feedback | No haptic feedback during onboarding (unlike PuzzleScreen which has haptics on cell tap and number entry). Inconsistent experience. | Medium | Mirror PuzzleScreen's haptic feedback in OnboardingScreen for cell taps and number inputs.
Progress Indicator | No indication of how many onboarding puzzles remain (1 of 3, 2 of 3, etc.). | Medium | Add a step indicator (dots or '1/3') at the top of OnboardingScreen.
HOME SCREEN
Visual Hierarchy | Streak display, status chips, countdown, difficulty selector, and Play button are all stacked vertically with similar visual weight. No clear focal point or CTA hierarchy. | High | Make the Play button larger and more prominent (use tertiary/amber CTA color). Reduce visual weight of countdown and status chips. Consider a card-based layout.
Streak at Zero | Streak displays '0 days streak' with a pulsing flame for new users. A pulsing flame on zero feels odd and discouraging. | Medium | Hide streak section or show an encouraging message like 'Start your streak today!' when streak is 0. Animate flame only when streak >= 1.
Completed Puzzle UX | When all 3 puzzles are completed, the Play button is still enabled but there's no new content. Users can replay completed puzzles with no differentiation. | High | Disable Play or show 'All done for today!' state. If replay is allowed, label it 'Replay' and don't count it toward streak/stats.
Countdown Timer | Countdown to midnight shown as HH:MM:SS with seconds ticking. This creates urgency/anxiety that's misplaced for a daily casual puzzle. | Low | Show approximate time: 'New puzzles in ~5 hours' or just 'New puzzles tomorrow'. Remove the seconds ticker.
Footer Link | 'More by dgeek' is a plain text with no action. No link, no tap handler. Dead UI element. | Medium | Either make it tappable (link to a portfolio/store page) or remove it entirely.
Scroll Behavior | HomeScreen has no scroll. On small devices (360dp width, compact height), content may clip below the Play button. | High | Wrap content in a verticalScroll modifier. Test on compact devices (e.g., Pixel 4a).
PUZZLE SCREEN
No Back/Exit Button | PuzzleScreen has no visible back button or way to exit mid-puzzle. Users must rely on system back gesture. | High | Add a top app bar with a back arrow and the difficulty label. Consider a pause/menu icon.
Timer Placement | Elapsed timer is a small labelLarge text at the top with minimal padding. Easy to miss and doesn't feel like a game timer. | Medium | Style the timer more prominently — consider a monospace font, slightly larger size, or a subtle container/chip.
No Undo Functionality | Users can only clear the current cell. No undo button for reverting the last move. Common in puzzle games. | High | Add an undo button alongside the clear button on the NumberPad. Track move history in PuzzleViewModel.
Error Feedback | Sum indicators change color (green/red/gray) but there's no animation or emphasis when a sum goes from gray to red. Easy to miss. | Medium | Add a brief shake or color-flash animation when a sum indicator turns red (over-target). Helps users catch mistakes.
Completion Experience | Completion shows a text banner 'Puzzle complete! 🎎' and hides the number pad. No share button, no stats summary, no next-puzzle prompt. | Critical | Show a completion card/bottom sheet with: solve time, difficulty, share button, 'Next puzzle' or 'Back to Home' CTAs. This is the key retention moment.
Grid Touch Target | Tap detection is calculated from raw Canvas coordinates. On 3x3 grids the cells are large, but on 5x5 medium puzzles cells may be small for fat-finger users. | Medium | Ensure minimum 44dp touch target per cell. On 5x5 grids, consider making the grid take more vertical space or add pinch-to-zoom.
Number Pad Sizing | NumberPad buttons are 48dp with 4dp spacing. On Medium difficulty (9 buttons + clear = 10 buttons), this gets cramped on narrow phones. | High | For 9+ buttons, switch to a 2-row layout (5+5 or 5+4+clear). Or use a 3x3+1 grid layout that's more thumb-friendly.
No Pencil/Notes Mode | No way to pencil in candidate numbers for a cell. Standard feature in number puzzle games (Sudoku, etc.). | Medium | Add a pencil/notes toggle that lets users mark possible values in a cell corner. Important for Medium difficulty.
VISUAL DESIGN & THEME
Dark Mode Grid | OLED dark theme defined (OledBlack #090909) but GridRenderer uses theme-derived colors. Given cells (primaryContainer) may have low contrast against dark surface. | High | Audit and test dark mode contrast ratios. Ensure given vs. user cells are distinguishable. Target WCAG AA (4.5:1 contrast ratio).
Brand Identity | App icon, splash screen, and in-app title are text-only ('SumGrid'). No logo or visual mark. Weak brand recall. | Medium | Design a simple logomark (e.g., a stylized grid with sum symbols) for the app icon, splash, and home screen.
Color Monotony | Deep indigo dominates all surfaces (primary, primaryContainer, gradient). Amber accent is only used for streak and cell selection. Overall feel is monochromatic. | Low | Use amber/warm-amber more strategically for CTAs, achievements, and interactive elements. The tertiary palette is underutilized.
Animation Polish | Celebration animation (scale 1.0→1.2→1.0 per cell) is subtle. For a game completion moment, it feels underwhelming. | Medium | Add confetti particles, a sound effect, or a more dramatic visual celebration. This is the reward moment.
ACCESSIBILITY
Font Scaling | Typography uses fixed sp values. If a user has large font accessibility settings, the UI may overflow or clip. | High | Test with 200% font scale. Ensure HomeScreen and NumberPad adapt without breaking layout.
Screen Reader Nav | Grid has invisible Box overlays for TalkBack, but navigation order may not be intuitive (reads all cells before reaching number pad). | Medium | Add traversal groups and focus ordering so TalkBack moves logically: timer → grid → number pad. Add 'puzzle complete' announcement.
Motion Sensitivity | Pulsing flame animation runs infinitely with no respect for 'Reduce motion' accessibility setting. | Medium | Check system's reduceMotion preference. Disable animations (flame pulse, cell selection spring) when enabled.
ENGAGEMENT & RETENTION
No Statistics Screen | No way to view solve history, average times, best times per difficulty, or completion rate. | High | Add a Stats screen accessible from Home: total puzzles solved, avg/best times per difficulty, completion calendar heatmap.
Badge Visibility | StreakBadges (Weekly Warrior, Monthly Master, etc.) are defined in code but never displayed in the UI. Invisible rewards. | Critical | Display earned badges on the Home screen or a dedicated achievements section. Show locked badges to motivate progression.
No Daily Notification | No push notification to remind users about today's puzzle. Key retention mechanic for daily games. | High | Add an opt-in daily reminder notification (e.g., 'Your daily SumGrid is ready!') at a user-chosen time.
Share Card Timing | ShareCardGenerator exists but there's no share button in the UI after puzzle completion. | Critical | Add a prominent 'Share' button on the completion card. The share system is built but not wired to the UI.
No Difficulty Progression | Only 3 static difficulty levels. No Hard/Expert modes. Players who master Medium have no next challenge. | Medium | Plan Hard (6x6) and Expert (7x7) difficulties. Consider weekly challenge puzzles or timed modes for variety.
Replay Value | Once all 3 daily puzzles are done, there's nothing else. No archive, no practice mode, no random puzzles. | High | Add a 'Practice' mode with unlimited random puzzles (non-streak-counted). Or a puzzle archive of past dailies.
TECHNICAL UX
State Persistence | If the app is killed mid-puzzle, progress may be lost. No visible auto-save indicator. | High | Ensure puzzle state persists on every cell change. Show a subtle auto-save indicator or confirm state restore on relaunch.
Loading States | HomeScreen shows CircularProgressIndicator. PuzzleScreen shows 'Loading puzzle...' text. Inconsistent loading UX. | Low | Unify loading states. Use a branded skeleton/shimmer effect instead of generic spinner.
Landscape Support | No landscape layout handling. On tablets or landscape phones, the vertical Column layout will look stretched and odd. | Medium | Add landscape layout: grid on left, number pad on right. Or lock to portrait with a clear manifest declaration.
In-App Review | InAppReviewTrigger is implemented but trigger conditions aren't visible. May fire at wrong moments. | Low | Trigger review prompt after 3rd puzzle completion or 7-day streak (positive moments only). Never during gameplay.

## Task Backlog
SumGrid — Prioritized UX/UI Improvement Backlog
Sorted by impact × effort. Work top-to-bottom for maximum user value.
# | Task | Priority | Effort | Impact | Description | Screen / Component
1 | Wire share button to completion screen | P0 | S | High | ShareCardGenerator and ShareIntentLauncher exist but no UI triggers them. Add a Share button to the puzzle completion banner. | PuzzleScreen
2 | Display earned streak badges | P0 | S | High | StreakBadge enum (Weekly Warrior, Monthly Master, etc.) is defined but never rendered. Show badges on HomeScreen. | HomeScreen
3 | Add skip option to onboarding | P0 | S | High | Let users skip the 3-day onboarding sequence. Add a 'Skip tutorial' text button on OnboardingScreen. | OnboardingScreen
4 | Add rules explanation to onboarding | P0 | S | High | Add a brief text card or coach marks explaining sum-grid rules before the first puzzle. | OnboardingScreen
5 | Add back/exit button to puzzle screen | P0 | S | High | Add TopAppBar with back navigation and difficulty label. Users currently rely on system back gesture only. | PuzzleScreen
6 | Build completion card / bottom sheet | P0 | M | High | Replace the text banner with a proper completion card: solve time, difficulty badge, Share button, Next Puzzle / Home CTAs. | PuzzleScreen
7 | Add undo functionality | P1 | M | High | Add undo button to NumberPad. Track move history stack in PuzzleViewModel. Essential for puzzle games. | PuzzleScreen, NumberPad
8 | 2-row number pad for Medium difficulty | P1 | M | High | 9 buttons + clear in a single row is too cramped on narrow phones. Switch to 2-row grid layout when maxVal >= 7. | NumberPad
9 | Add statistics screen | P1 | M | High | New screen: total solved, avg/best times per difficulty, completion calendar. Accessible from HomeScreen. | New: StatsScreen
10 | Make HomeScreen scrollable | P1 | S | High | Wrap Column content in verticalScroll. Prevents clipping on compact devices (360dp width). | HomeScreen
11 | Daily reminder notification | P1 | M | High | Opt-in push notification: 'Your daily SumGrid is ready!' at user-chosen time. Key for daily game retention. | New: NotificationManager
12 | Practice / random puzzle mode | P1 | L | High | Unlimited non-daily puzzles for users who finish all 3 dailies. Doesn't count toward streak. | New: PracticeScreen
13 | All-done state for HomeScreen | P1 | S | Medium | When all 3 puzzles completed, show celebratory state instead of active Play button. 'All done! See you tomorrow.' | HomeScreen
14 | Enhanced celebration animation | P2 | M | Medium | Add confetti particles or more dramatic visual/sound on puzzle completion. Current scale animation is too subtle. | CelebrationAnimation
15 | Dark mode contrast audit | P1 | M | High | Test OLED dark theme contrast ratios. Ensure given vs user cells are distinguishable. Target WCAG AA 4.5:1. | GridRenderer, Theme
16 | Reduce motion accessibility | P2 | S | Medium | Respect system 'Reduce motion' setting. Disable flame pulse, cell spring, and celebration animations. | HomeScreen, GridRenderer
17 | Error indicator animation | P2 | S | Medium | Add shake or flash when sum indicator turns red. Helps users notice mistakes without constant checking. | GridRenderer
18 | Brand logomark design | P2 | M | Medium | Design a simple visual mark for app icon, splash, and HomeScreen title area. Currently text-only. | App-wide
19 | Pencil/notes mode | P2 | L | Medium | Toggle to mark candidate numbers in cell corners. Standard in number puzzles. Most valuable for Medium difficulty. | PuzzleScreen, GridRenderer
20 | Onboarding progress indicator | P2 | S | Medium | Show step dots or '1/3' counter during onboarding sequence. | OnboardingScreen
21 | Fix zero-streak display | P2 | S | Medium | Hide pulsing flame when streak=0. Show 'Start your streak today!' instead of '0 days streak'. | HomeScreen
22 | Make footer link tappable | P2 | S | Low | Either link 'More by dgeek' to a portfolio URL or remove the dead text. | HomeScreen
23 | Font scaling test & fix | P1 | M | High | Test with 200% font accessibility scale. Fix any overflow/clipping in HomeScreen and NumberPad. | App-wide
24 | Landscape layout or lock | P2 | M | Medium | Either add responsive landscape layout (grid left, pad right) or lock to portrait in manifest. | App-wide
25 | Timer styling upgrade | P3 | S | Low | Use monospace font for puzzle timer. Add subtle chip/container. Make it feel more like a game timer. | PuzzleScreen
26 | Friendly countdown format | P3 | S | Low | Change midnight countdown from 'HH:MM:SS' to 'New puzzles in ~5 hours' to reduce anxiety. | HomeScreen
27 | Unified loading states | P3 | S | Low | Replace CircularProgressIndicator and text with a branded shimmer/skeleton effect. | HomeScreen, PuzzleScreen
28 | Screen reader focus ordering | P2 | M | Medium | Add traversal groups so TalkBack reads: timer → grid → number pad. Add 'puzzle complete' announcement. | PuzzleScreen
29 | Smart in-app review trigger | P3 | S | Low | Trigger review after 3rd completion or 7-day streak. Never during active gameplay. | App-wide
30 | Hard & Expert difficulty levels | P2 | L | Medium | Add 6x6 Hard and 7x7 Expert puzzles for players who master Medium. Extends game longevity. | Difficulty, Engine
31 | State persistence indicator | P1 | M | High | Ensure puzzle auto-saves on every cell change. Show subtle save indicator. Restore state on relaunch. | PuzzleViewModel
Priority: P0 = Do first (blocks retention) ¦ P1 = Next sprint ¦ P2 = Polish ¦ P3 = Nice-to-have Effort: S = Small (<4h) ¦ M = Medium (4-16h) ¦ L = Large (16h+)

## Sprint Plan
Suggested Sprint Plan
Reference | Task | Estimate
SPRINT 1: Quick Wins & Critical Fixes (1 week)
Task #1 | Wire share button to completion screen | ~2h
Task #2 | Display earned streak badges on Home | ~3h
Task #3 | Add skip to onboarding | ~2h
Task #4 | Add rules explanation | ~3h
Task #5 | Add back button to PuzzleScreen | ~2h
Task #10 | Make HomeScreen scrollable | ~1h
Task #13 | All-done state for HomeScreen | ~2h
| Sprint 1 total estimate | ~15h
SPRINT 2: Core Game UX (1-2 weeks)
Task #6 | Build completion card / bottom sheet | ~8h
Task #7 | Add undo functionality | ~6h
Task #8 | 2-row NumberPad for Medium | ~4h
Task #15 | Dark mode contrast audit & fixes | ~6h
Task #23 | Font scaling accessibility test & fix | ~6h
Task #31 | State persistence & auto-save | ~6h
| Sprint 2 total estimate | ~36h
SPRINT 3: Retention & Engagement (2 weeks)
Task #9 | Statistics screen | ~12h
Task #11 | Daily reminder notifications | ~8h
Task #12 | Practice / random puzzle mode | ~16h
Task #14 | Enhanced celebration animation | ~6h
| Sprint 3 total estimate | ~42h
SPRINT 4: Polish & Accessibility (1-2 weeks)
Task #16 | Reduce motion accessibility | ~3h
Task #17 | Error indicator animation | ~3h
Task #19 | Pencil/notes mode | ~16h
Task #24 | Landscape layout or lock | ~6h
Task #28 | Screen reader focus ordering | ~4h
Task #30 | Hard & Expert difficulty levels | ~16h
| Sprint 4 total estimate | ~48h